## Milestones
ID | At Risk? | Deliverable | Assigned to | Week | Date | Status | Sign Off
1.1 | No | IPP Presentation | All | S1, Week 4 | Monday 14/10/2024 | incomplete
1.2 | No | IPP Gate Review | All | S1, Week 4 | Thursday 17/10/2024 | incomplete
2.1.1 | Yes | First Propellar Thrust Test | Louis Allpress | S1, Week 4 | tbd | incomplete
1.3 | No | IPP Report | All | S1, Week 5 | Thursday 24/10/2024 | incomplete
2.1.2 | Yes | Part order form sent out | Sebastien C-B | S1, Week 6 | Friday 01/11/24 | incomplete
2.1.3 | Yes | Motor Arm Deflection Test | Taylor Keenan | S1, Week 9 | tbd | incomplete
2.1.4 | No | Sony a5000 camera Inspection | Michael Parker | S1, Week 10 | tbd | incomplete
2.1 | No | FDR Presentation | All | S1, Week 11 | Monday 02/12/2024 | incomplete
2.2 | No | FDR Gate Review | All | S1, Week 11 | Thursday 05/12/24 | incomplete
2.3 | No | FDR Report | All | S1, Week 12 | Sunday 15/12/2024 | incomplete
3.1.1 | Yes | PID Control Tune Test | Louis Allpress | S2, Week 3 | tbd | incomplete
3.1.2 | No | Ardupilot flight plan inspection | Michael Parker | S2, Week 6 | tbd | incomplete
3.1.3 | Yes | Platform GSD Test | Thomas Jakeman | S2, Week 7 | tbd | incomplete
3.1.4 | No | Final Spending Inspection | Sebastien C-B | S2, Week 8 | tbd | incomplete
3.1.5 | No | Final Platform Weight Inspection | Michael Parker | S2, Week 8 | tbd | incomplete
3.1 | No | FTRR Presentation | All | S2, Week 9 | tbd | incomplete
3.2 | No | FTRR Gate Review | All | S2, Week 10 | Monday 31/03/25 | incomplete
3.3 | No | FTRR Report | All | S2, Week 11 | tbd | incomplete
4.1.1 | Yes | Camera Angle and control Demonstration | Thomas Jakeman | S2, Week 11 | tbd | incomplete
4.1 | Yes | Flight Test Evaluation | All | S2, Week 12 | Monday 05/05/24 | incomplete

## Milestones at risk
ID | Description | Assigned to | Risk Register Progress | Signed Off
2.1.1 | First Propellar Thrust Test | Louis Allpress | complete
2.1.2 | Part order form sent out | Sebastien CB | complete
2.1.3 | Motor Arm Deflection Test | Taylor Keenan | complete
3.1.3 | Platform GSD Test | Thomas Jakeman | complete
4.1.1 | Camera Angle and control Demonstration | Thomas Jakeman | complete
4.1.0 | Flight Test Evaluation | All | complete