## Sheet1
ID | type | At Risk? | Description | Assigned to | Duration | Week | Status | Sign Off | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Xmas | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
| Task | No | Backround research | All | 1 Day | S1, Week 1 | In Progress
| Task | No | Team Role Selection | All | 1 Day | S1, Week 1 | Complete | Michael Parker
| Task | No | Requirements Breakdown | All | 3 Days | S1, Week 2 | Complete | Michael Parker
| Task | No | Platform Selection | All | 1 Day | S1, Week 2 | Complete | Michael Parker
| Task | Yes | Avionic selection | Louis Allpress | 5 Days | S1, Week 2 | Complete | Michael Parker
| Task | No | Airframe CAD Concept formulation | Taylor Keenan | 9 Days | S1, Week 3 | Complete | Michael Parker
| Task | No | Gimbal CAD Conceptual Design Formulation | Thomas Jakeman | 9 Days | S1, Week 3 | Complete | Michael Parker
| Task | No | Materials research | Sebastien C-B | 2 Days | S1, Week 3 | Complete | Michael Parker
| Task | No | Material Selection | Taylor Keenan | <1 Day | S1, Week 3 | Complete | Michael Parker
| Task | No | Initial Finite element Analysis | Sebastien C-B | 2 Days | S1, Week 3 | Complete | Michael Parker
| Task | No | Initial Momentum Theory | Chaz Love | 4 Days | S1, Week 3 | Complete | Michael Parker
| Task | Yes | Budget set | Michael Parker | 1 Day | S1, Week 3 | Complete | Michael Parker
| Milestone | No | End Of Conceptual Design | All | NA | S1, Week 3 | incomplete
| Milestone | No | IPP Presentation | All | 12 Days | S1, Week 4 | Complete | Michael Parker
| Milestone | No | IPP Gate Review | All | NA | S1, Week 4 | Complete | Michael Parker
| Task | Yes | First Propellar Thrust Test | Louis Allpress | <1 Day | S1, Week 4 | incomplete
| Milestone | No | IPP Report | All | 7 Days | S1, Week 5 | incomplete
| Task | Yes | Part order form sent out | Sebastien C-B | 1 Day | S1, Week 6 | incomplete
| Milestone | No | End of Preliminary Design Phase | All | NA | S1, Week 8 | incomplete
| Task | Yes | Motor Arm Deflection Test | Taylor Keenan | <1 Day | S1, Week 9 | incomplete
| Milestone | No | End Of Detail Deisgn Phase | All | NA | S1, Week 10 | incomplete
| Milestone | No | FDR Presentation | All | 35 Days | S1, Week 11 | incomplete
| Milestone | No | FDR Gate Review | All | NA | S1, Week 11 | incomplete
| Milestone | No | FDR Report | All | 7 Days | S1, Week 12 | incomplete
| Milestone | No | End Of Production Phase | All | NA | S2, Week 2 | incomplete
| Task | Yes | PID Control Tune Test | Louis Allpress | <1 Day | S2, Week 4 | incomplete
| Task | No | Ardupilot flight plan inspection | Michael Parker | <1 Day | S2, Week 6 | incomplete
| Milestone | No | End Of Integration Phase | All | NA | S2, Week 7 | incomplete
| Task | No | Final Spending Inspection | Sebastien C-B | <1 Day | S2, Week 8 | incomplete
| Task | No | Final Platform Weight Inspection | Michael Parker | <1 Day | S2, Week 8 | incomplete
| Milestone | No | FTRR Presentation | All | 63 Days | S2, Week 9 | incomplete
| Milestone | No | FTRR Gate Review | All | NA | S2, Week 10 | incomplete
| Milestone | No | End Of Testing Phase | All | NA | S2, Week 10 | incomplete
| Milestone | No | FTRR Report | All | 7 Days | S2, Week 11 | incomplete
| Task | Yes | Camera Angle and control Demonstration | Thomas Jakeman | 1 Day | S2, Week 11 | incomplete
| Milestone | Yes | Flight Test Evaluation | All | NA | S2, Week 12 | incomplete