## Milestones
ID | type | At Risk? | Description | Assigned to | Duration | Week | Status | Sign Off
1 | Milestone | No | Conceptual Design | All | 28 Days |  | In Progress
1.1 | Task | No | Backround research | All | 1 Day | S1, Week 1 | In Progress
1.2 | Task | No | Team Role Selection | All | 1 Day | S1, Week 1 | Complete | Michael Parker
1.3 | Task | No | Requirements Breakdown | All | 3 Days | S1, Week 2 | Complete | Michael Parker
1.4 | Task | No | Platform Selection | All | 1 Day | S1, Week 2 | Complete | Michael Parker
1.5 | Task | Yes | Avionic selection | Louis Allpress | 5 Days | S1, Week 2 | Complete | Michael Parker
1.6 | Task | No | Airframe CAD Concept formulation | Taylor Keenan | 9 Days | S1, Week 3 | Complete | Michael Parker
1.7 | Task | No | Gimbal CAD Conceptual Design Formulation | Thomas Jakeman | 9 Days | S1, Week 3 | Complete | Michael Parker
1.8 | Task | No | Materials research | Sebastien C-B | 2 Days | S1, Week 3 | Complete | Michael Parker
1.9 | Task | No | Material Selection | Taylor Keenan | <1 Day | S1, Week 3 | Complete | Michael Parker
1.1 | Task | No | Initial Finite element Analysis | Sebastien C-B | 2 Days | S1, Week 3 | Complete | Michael Parker
1.11 | Task | No | Initial Momentum Theory | Chaz Love | 4 Days | S1, Week 3 | Complete | Michael Parker
1.12 | Task | Yes | Budget set | Michael Parker | 1 Day | S1, Week 3 | Complete | Michael Parker
1.13 | Task | No | IPP Presentation | All | 12 Days | S1, Week 4 | incomplete
1.14 | Milestone | No | IPP Gate Review | All | NA | S1, Week 4 | incomplete
1.15 | Task | No | IPP Report | All | 7 Days | S1, Week 5 | incomplete
2 | Milestone | No | Preliminary Design | All | 22 Days |  | incomplete
2.1 | Task | Yes | First Propellar Thrust Test | Louis Allpress | <1 Day | S1, Week 4 | incomplete
2.2 | Task | Yes | Part order form sent out | Sebastien C-B | 1 Day | S1, Week 6 | incomplete
2.3 | Task | Yes | Motor Arm Deflection Test | Taylor Keenan | <1 Day | S1, Week 9 | incomplete
3 | Milestone | No | Detail Design | All | 27 Days |  | incomplete
3.1 | Task | No | Sony a5000 camera Inspection | Michael Parker | <1 Day | S1, Week 10 | incomplete
3.2 | Task | No | FDR Presentation | All | 35 Days | S1, Week 11 | incomplete
3.3 | Milestone | No | FDR Gate Review | All | NA | S1, Week 11 | incomplete
3.4 | Task | No | FDR Report | All | 7 Days | S1, Week 12 | incomplete
4 | Milestone | Yes | Production | All | 56 Days |  | incomplete
4.1 | Task | Yes | PID Control Tune Test | Louis Allpress | <1 Day | S2, Week 3 | incomplete
4.2 | Task | No | Ardupilot flight plan inspection | Michael Parker | <1 Day | S2, Week 6 | incomplete
4.3 | Task | Yes | Platform GSD Test | Thomas Jakeman | 2 Days | S2, Week 7 | incomplete
4.4 | Task | No | Final Spending Inspection | Sebastien C-B | <1 Day | S2, Week 8 | incomplete
4.5 | Task | No | Final Platform Weight Inspection | Michael Parker | <1 Day | S2, Week 8 | incomplete
4.6 | Task | No | FTRR Presentation | All | 63 Days | S2, Week 9 | incomplete
4.7 | Milestone | No | FTRR Gate Review | All | NA | S2, Week 10 | incomplete
4.8 | Task | No | FTRR Report | All | 7 Days | S2, Week 11 | incomplete
4.9 | Task | Yes | Camera Angle and control Demonstration | Thomas Jakeman | 1 Day | S2, Week 11 | incomplete
5 | Milestone | Yes | Flight Test Evaluation | All | NA | S2, Week 12 | incomplete

## Sheet3
Start Date | Due Date
2024-09-25 | 2024-10-24
2024-09-30 | 2024-10-24
2024-09-25 | 2024-09-25
2024-09-30 | 2024-10-03
2024-09-30 | 2024-10-01
2024-09-30 | 2024-10-05
2024-10-07 | 2024-10-11
2024-10-07 | 2024-10-11
2024-10-06 | 2024-10-08
2024-10-09 | 2024-10-11
2024-10-06 | 2024-10-10
2024-10-07 | 2024-10-11
2024-10-02 | Monday 14/10/2024
NA | Thursday 17/10/2024
tbd | tbd
Thursday 24/10/2024 | Thursday 24/10/2024
2024-10-25 | 2024-11-17
Friday 01/11/24
tbd | tbd
2024-11-18 | 2024-12-15
tbd | tbd
Monday 02/12/2024 | Monday 02/12/2024
Thursday 05/12/24 | Thursday 05/12/24
Sunday 15/12/2024 | Sunday 15/12/2024
2025-02-01 | 2025-03-24
tbd | tbd
tbd | tbd
tbd | tbd
tbd | tbd
tbd | tbd
tbd | tbd
Monday 31/03/25
tbd | tbd
tbd | tbd
Monday 05/05/24

## Gantt
| week 1 | week 2 | week 3 | week 4 | week 5 | week 6 | week 7 | week 8 | week 9 | week 10 | week 11 | week 12
task1
task2
task3
task4
task5
task6
task7
task8
task9
task10
task11
task12
task13
task14
task15
task16
task17

## Critical Path
Task
Conceptual design completion
Preliminary design Completion
Detail Design Completion
Conceptual design completion
Product completion
Test

## Milestones at risk
ID | Description | Assigned to | Risk Register Progress | Signed Off
1.5 | Avionic selection | Louis Allpress | complete | Michael Parker
1.12 | Budget set | Sebastien CB | complete | Michael Parker
2.1 | First Propellar Thrust Test | Louis Allpress | complete | Michael Parker
2.2 | Part order form sent out | Sebastien CB | incomplete
2.3 | Motor Arm Deflection Test | Taylor Keenan | incomplete
4.1 | PID tune test | Louis Allpress | incomplete
4.3 | Platform GSD Test | Thomas Jakeman | incomplete
4.9 | Camera Angle and control Demonstration | Thomas Jakeman | incomplete

## Risk Register
ID | Date raised | Risk Description | Probability | Impact | Severity | Mitigation | Contingency plan | Signed off by
| 2024-10-11 | Illness of team member | 7 | 3 | 21 | following WHO guidelines
| 2024-10-11 | Team member Injury | 1 | 4 | 4 | don’t be clumsy you silly bitch
| 2024-10-11 | Mentor weekly inavailability | 6 | 2 | 12 | Before scheduled meeting, ensure availabilty | arrange for alternate schedule for the affected weeks
| 2024-10-11 | Team member timetable clash | 2 | 3 | 6
| 2024-10-11 | Part Manufacturing error | 6 | 8 | 48
| 2024-10-11 | Project files save Corruption/overwrite | 4 | 10 | 40 | Have muliple backups of main repository
| 2024-10-12 | HHTC room avialability | 6 | 6 | 36 | leave plent of time to complete the tasks
| 2024-10-12 | 3D Printing Availability | 8 | 4 | 32 | Get required 3D printing CAD drawings completed early
| 2024-10-12 | Lipo battery explodes | 5 | 10 | 50 | Discharge the Battery to resting charge, place in sandbag